## First Week
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring: Finish and submit complete proposals for the team projects
Scrum Master this week: Alec Pippas
Week: 2/1/24-2/7/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? |  | Found and explored www.studenthousing.org & Found and explored www.roomster.com | Filled out availablility schedule. Began tracking contributions in the Daily Scrum notes document. | Meet with team to finalize the project proposal. | Submitted Final Project Proposal and 1st week for DailyScrumNotes
| What will you work on to complete today? | Research similar websites/businesses that help other individuals find roommates. Research similar websites/businesses that help students find accomodative housing. | Modify availability schedule template that each teammate will fill-out at the beginning of each week so we can best coordinate team meetings. | Review and edit project description. Add bullet points to the MVP and MLP sections of the proposal. Meet with team at 4pm to finalize our detailed project proposal. Formalized how are we | Finish the daily scurm note and finalize system for recording daily Scrum notes with the team. | Attend class and prepare for Week 3 Assignment
| Do you have any obstacles? | no | Finding the best times we can all meet generally in a given week. Alot of teammates have conflicting schedules unfortunately. | Teammate dropped the class so we will likely need to find another teammate or inquire with the professor to address our decreased bandwidth. | no | Missing teammate. Not sure if we will get another one so we will have to make modification to each individual's contribution.
Vorrapard Kumthongdee | What did you complete yesterday? | Re-read the project ideas from last week | Went through the project proposal template to see what is needed for this week | Helped prepare the shared Google Drive for the team | Helped team wrap up the project proposal
| What will you work on to complete today? | Read the project proposal template | Organize a shared working space and files | Getting ready to vote the final proposal | Start looking into frameworks
| Do you have any obstacles? | no | no | A team member dropped the class - need to find a new one | no | no
Faiyaad Hossain | What did you complete yesterday? | Transferred proposal template onto a editable Google Docs file so we can work on it together. | Added core features to MVP section of proposal. | Looked at competing platforms and made a list of MLP features, such as an interactive map and creating a new user class for landlords | Finalized proposal; added two different personas and refined the project description to have more of a focus | Created GitHub Repo
| What will you work on to complete today? | Start looking at our list of proposed features to categorize which ones are for MLP vs MVP. | Look at similar products found by other team members and get an understanding of the standard features as a reference point on how we should craft our project. | Meet with team at 4pm to discuss project name and flesh out the final proposal. | Create a new GitHub repository since the original repo owner dropped the class | Meet with team to discuss tech stack and resources for learning Django, React, etc. Share GitHub with the rest of the team
| Do you have any obstacles? |  |  | One of our team members had to drop the class, so we will possibly have to adjust the scope of our project
Jeremy Freeman | What did you complete yesterday? | Met with team to review initial proposal ideas | Established team schedule and began work on proposal | Updated MVP/MLP/Nice-to-have sections of proposal | Chose project name, started brainstorming CRUD and user personas
| What will you work on to complete today? | Meet with team to strategize and plan our schedule for the upcoming week, solidify project description on proposal document | Reviewed similar products discovered by teammates, brainstormed and finalized ideas for MVP/MLP/Nice-to-have during team meeting | Meet with team at 4pm, vote on a project name, begin brainstorming for CRUD features. | Finalize CRUD section and proposal with teammates
| Do you have any obstacles? |  | It can be challenging to decide which features are essential and which ones would be nice, teammates might disagree on this | Teammate dropped class

## Sprint 1 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring: Produce requirements for team projects. The team is expected to collaborate, review documents and produce agreed-upon requirements in form of user stories.
Scrum Master this week: Alec Pippas
Week: 2/8/24-2/14/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | planned teammeeting for today to convert proposal features to various user stories | Met with the team last night and we came up with the first draft of our user stories. We planned a meeting for next Monday to review and finalize our user stories for submission. | Reviewed the professor's feedback on the project proposal. | Postponed team meeting to 5pm today. | Most of the feature modifications/additions from the professor's feedback were concidentally added in new user stories including the update/remove listing feature, the ability for students to list their current apartments for new roommates or subleasing, and the save listing feature. However, we reworded some user stories, added more acceptability criteria, and assessed the user stories for overlap.
| What will you work on to complete today? | Teammeeting at 6pm to create user stories/requirements as part of Assignment 3. | Review the professor's feedback on the project proposal. | Meet with team to finalize the user stories and the professor's feedback and incorporate any chagnes to our first draft. | Meet with team at 5pm to finalize user stories and incorporate professor's feedback. | Attend class and meet with team afterwards to plan for our week 4 assignment.
| Do you have any obstacles? | Need to verify correct sizing of user stories. |  | We were not able to find a time that we could all meet on Monday so we rescheduled the meeting for Tuesday. | whether or not to incorporate our map feature into our prototype delivery for this class given the reduced team capacity.
Vorrapard Kumthongdee | What did you complete yesterday? | Sprint with the team | Finished the first draft of the User stories | Watched videos on how to use Github | Watched a little video on React | Wraped up the user stories and created a slide
| What will you work on to complete today? | Meet up to brainstrom the User stories | Learn how to use Github and Frameworks | Learn how to use Django/React | Finalize User stories with the team/ Sprint review slide | Team meeting to plan the next assignment
| Do you have any obstacles? | no | no | no | no | no
Faiyaad Hossain | What did you complete yesterday? | Created a new GitHub repo and added teammates as collaborators. | Created user stories with teammates | Linked a few tutorial videos on the team's Discord channel and watched a GitHub/Git tutorial | Watched video on Django - project creation | Finalized user stories for this week's sprint
| What will you work on to complete today? | Meet with team at 6pm to create user stories (longer meeting) | Look up tutorials/resources for GitHub and Django/React to get familiar with the technology stack for the project | Watch more tutorials on Django/React | Meet with team at 5pm to finalize user stories
Do you have any obstacles?
Jeremy Freeman | What did you complete yesterday? | Scheduled team meeting | Meet with team, discuss user stories | Meet with team to write up user stories | Watch Django/React tutorials as preparation for later on | Meet with team to revise and refine user stories
| What will you work on to complete today? | Meet with team, brainstorm user stories | Begin writing first draft of user stories | Watch Django/React tutorials as preparation for later on, review user stories | Meet with team to revise and refine user stories | Finalize user stories
Do you have any obstacles?

## Sprint 1 - Week 2
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring: Produce requirements for team projects. The team is expected to collaborate, review documents and produce agreed-upon requirements in form of user stories.
Scrum Master this week: Alex Pippas
Week: 2/15/24 - 2/21/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Meet with team after class to plan the week out and set up teammeetings. | Studied Djanjo and reviewed Week 4 Lecture Presenation. | Studied the Djanjo tutorial. | Started the sequence diagrams and the delegated each diagram to a teammember to bring to today's meeting.
| What will you work on to complete today? | Study Djanjo tutorial and review the concpets from last class in preparation of tomorow's meeting. | Meet with team to study use cases from class and create the use case diagram. | Meet with team to finalize the use case diagram. begin the Sequence Diagrams. | Meet with team at night to complete the sequence diagrams.
| Do you have any obstacles? | No. | No. | Yes we were confused about some of the sequence diagram elements and needed to reconvene to finish the sequence diagrams. | Potentially could add a 4th sequence diagram.
Vorrapard Kumthongdee | What did you complete yesterday? | Discuss the next assignment with team | Did a little of study | Drafted UML | Finished UML, drafted sequance diagram
| What will you work on to complete today? | Study about UML and sequence diagram | Coordinate with the team to initialize week 4 assignment | Finalize UML and start sequence diagram | finalize sequence diagram
| Do you have any obstacles? | no | no | no | no
Faiyaad Hossain | What did you complete yesterday? | Discussed backlog items with team after class | Found UML diagrams and a good website draw.io to create diagrams | Started use-case diagram with team | Worked on sequence diagrams, watched more django tutorials
| What will you work on to complete today? | Look up UML diagram examples for different applications | Meet with team to start working on diagrams | Refine use-case diagram, start on sequence diagrrams | Meet with team to finish sequence diagrams
| Do you have any obstacles? |  |  | Zenhub is giving us trial accounts, need to bring up to professor
Jeremy Freeman | What did you complete yesterday? | Scheduled team meeting | Prepared for team meeting and studied Django | Created use case diagram | Created sequence diagrams and finished use case diagram
| What will you work on to complete today? | Study use case diagrams for reference and watch Django tutorials | Meet with team to create use case diagram | Finish editing use case diagram and start creating sequence diagrams | Meet with team to finalize sequence diagrams
| Do you have any obstacles? |  |  | Having an issue setting up my Zenhub account

## Sprint 2 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring:
Scrum Master this week: Faiyaad Hossain
Week: 2/22/24 - 2/28/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Completed in-class ZenHub tutorial. Setup Zenhub workspace and linked each teammates' account to our team's Github repository. | Django tutorial. | Met with team. | Completed Sprint notes
| What will you work on to complete today? | Study Django and React tutorials in preparation of tomorrow's meeting. | Meeting with teammembers to finalize our Zenhub workspace and to plan for the next week. | React Tutorial. Check-in meeting with team. | Finish tutorials ahead of the start of next weeks sprint. | Attend class and prepare for the first "real" sprint with user story implentation work.
| Do you have any obstacles? | no | all teammembers need to finish the tutorials so we can begin implementing chosen user stories with code and enact a sprint for the assignment due on March 5th. | Team meeting was not required as we are all working individually. | no
Vorrapard Kumthongdee | What did you complete yesterday? | Get familiar with ZenHub | Django | Zenhub discussion | Django hands-on practice | Create a local skeleton for the project
| What will you work on to complete today? | Watch Django/React videos | Meeting to discuss how we organize Zenhub | Try to adapt the app with Django | Create a local skeleton for the project | sick
| Do you have any obstacles? | no | no | no | no | no
Faiyaad Hossain | What did you complete yesterday? | Set up Zenhub wit h team and integrated with GitHub | Watched another Django video | Continued watching tutorial videos | Was unable to allocate time to our project due to workload from anotherr class | Looked at sample React projects for frontend inspiration
| What will you work on to complete today? | Study Django/React | Meet with team briefly to touch base on sprint goals | Need to work on another class's assignment, but will try to watch another video on Django | Look at sample login pages from publicly available React projects to get an idea of how to implement ours | Meet with team during class and touch base on our first user story implementation
| Do you have any obstacles? | This week I have an assignment for another class which I will need to prioritize, given the deadline
Jeremy Freeman | What did you complete yesterday? | Got set up with Zenhub | Watched Django tutorials | Met with team, watched more Django tutorials | Started watching React videos | Watched Django and React tutorials
| What will you work on to complete today? | Study Django | Meet with team to review sprint goals and finish setting up Zenhub | Start studying React | Continue watching Django and React tutorials to prepare for next week | Attend class, discuss upcoming spring with team
| Do you have any obstacles? |  |  |  | Balancing studies with assignments from other classes

## Sprint 2 - Week 2
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring:
Scrum Master this week: Faiyaad Hossain
Week: 2/29/24 - 3/06/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Meet with team after class do plan the upcoming Sprint | n/a Zenhub trial expired | Meet with team. Mergered Save Listing and Advertise Listing User Stories given their strong interrelatedness. Reached out to our TA in regards to receiving a trial extension to Zenhub. | Completed Sprint Retrospective report. Faiyaad showed us the project framework he established (directories + files) and the implementation work he began on the Login User Story
| What will you work on to complete today? | Organize Zenhub (product backlog, sprint backlog), upload User Stories as Epics on Zenhub | Meet with team to polish our User Stories | Meet with team to prepare for in-class Sprint Demo and Sprint Retrospective. Continue the Django and React tutorials. | More Django and React Tutorials. Finish weekly scurm notes.
| Do you have any obstacles? | Zenhub trial is expiring. | We are all locked out of Zenhub and cannot use it to plan/manage our Sprints | My Django competency is not up to speed and I want to help the team more.
Vorrapard Kumthongdee | What did you complete yesterday? | sick | sick | sick | Backend for login page | Watched videos on django
| What will you work on to complete today? | meet with team to discuss zenhub | sick | Start looking into backend | Trying to implement database to store account info | Initialized Django database
| Do you have any obstacles? | zenhub expires | no | no | no | no
Faiyaad Hossain | What did you complete yesterday? | Met with team in class to discuss current sprint | Created backend folder | Created login/signup pages on frontend; pushed boilerplate code to GitHub | Met with team to create retrospective report | Watched Django tutorials
| What will you work on to complete today? | Create Django backend directory on local drive | Create frontend boilerplate code using React | Meet with team to go over the current code base and provide guidance | Start looking into building APIs in Django | Sprint Demo in Class
| Do you have any obstacles? | Zenhub is down, can't document sprint/user stories
Jeremy Freeman | What did you complete yesterday? | Met with team in class, established a plan for upcoming sprint | Watched Django + React tutorials | Watched Django + React tutorials | Met with team, assembled retrospective report | Watched Django + React tutorials
| What will you work on to complete today? | Watch Django + React tutorials | Watch Django + React tutorials, reviewed user stories | Meet with team to review boilerplate React code | Watch Django + React tutorials, prepare to begin developing back end with Django | Sprint demo presentation
| Do you have any obstacles? |  | Zenhub is down | Not super familiar with React yet, more study required | Still learning Django

## Sprint 3 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring:
Scrum Master this week: Faiyaad Hossain
Week: 3/07/24 - 3/13/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Sprint Demo in-class |  | Completed 2 Django and React tutorials
| What will you work on to complete today? |  | Complete Django & React Tutorials |  | Finished Github training
| Do you have any obstacles? | Team has Mid-terms during this week, so focusing on development work will be challenging generally lower priority for the team |  |  | Teammates and I too slammed with other midterm work.
Vorrapard Kumthongdee | What did you complete yesterday? | Pulled the Django database from the branch | Created UserProfile database model | Created Listing database model | Created Message database model | Created Favorite database model
| What will you work on to complete today? | UserProfile model | Listing model | Message model | Favorite model | merge the models to main branch
| Do you have any obstacles? | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms
Faiyaad Hossain | What did you complete yesterday?
What will you work on to complete today?
| Do you have any obstacles? | Focused on midterms/projects for other class; can't commit to SWE project this week | Focused on midterms/projects for other class; can't commit to SWE project this week | Focused on midterms/projects for other class; can't commit to SWE project this week | Focused on midterms/projects for other class; can't commit to SWE project this week | Focused on midterms/projects for other class; can't commit to SWE project this week
Jeremy Freeman | What did you complete yesterday?
What will you work on to complete today?
| Do you have any obstacles? | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms | Overwhelmed with midterms

## Sprint 3 - Week 2
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Spring Goal for this Spring:
Scrum Master this week: Jeremy Freeman
Week: 3/14/24 - 3/20/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday?
| What will you work on to complete today? | Spring Break | Spring Break | Spring Break | Spring Break | Spring Break
Do you have any obstacles?
Vorrapard Kumthongdee | What did you complete yesterday? | - | - | - | - | -
| What will you work on to complete today? | Spring break | Spring break | Spring break | Spring break | Spring break
| Do you have any obstacles? | - | - | - | - | -
Faiyaad Hossain | What did you complete yesterday? |  |  |  |  | Created backend API for login/authentication
| What will you work on to complete today? |  |  |  | Continue finishing login page user story (create backend) | Connect backend and frontend for login/authentication
| Do you have any obstacles? | Focused on midterms/projects for other class; can't commit to SWE project this week (until 3/18) | Focused on midterms/projects for other class; can't commit to SWE project this week (until 3/18) | Focused on midterms/projects for other class; can't commit to SWE project this week (until 3/18)
Jeremy Freeman | What did you complete yesterday?
What will you work on to complete today?
| Do you have any obstacles? | Overwhelmed with midterms | Overwhelmed with midterms | Spring break, traveling | Spring break, traveling | Spring break, traveling

## Sprint 3 - Week 3
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Connect backend and frontend for login page, start creating DB models for other pages (ie. Listing Page)
Scrum Master this week: Jeremy Freeman
Week: 3/21/24 - 3/27/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? |  | JavaScript tutorial on Codecademy. Part 9, 10 of Django Tutorial. | Spring "Breaked" | Completed 50% of Javascript tutorial on Codeacademy. | Cloned team's github repo locally.
| What will you work on to complete today? | Django/React Tutorial. Learn basic JavaScript | Spring Break | More Javascript tutorials to finish learning basics. | Meet with team later on to discuss in-class Sprint Demo, review weekly contributions, and complete the Sprint Retrospective report. | Sprint Demo in-class. Meet with team after class.
| Do you have any obstacles? | Don't know JavaScript |  | Need to finish | Need to create database schema diagram to help with backend database implementation.
Vorrapard Kumthongdee | What did you complete yesterday? | Initialized the Django skelleton and installed dependencies | attemped to create a model | created the board database | Re-cloning the master branch | successfully running both servers and connect them for the application
| What will you work on to complete today? | Create the board database | Create the board database | Pulling the main brance to my environment to merge the code | Pull the master branch and try running | push the user's profile database model to Github
| Do you have any obstacles? | Django used models instead of sql table | Django used models instead of sql table | there was a bug when pulling the repo to my environment. Some database tables are missing | no | no
Faiyaad Hossain | What did you complete yesterday? | Finished connecting login frontend and backend | Created logout functionality |  |  | Created retrospective report
| What will you work on to complete today? | Refine user interface and create logout mechanic | Work on retrospective report |  | Create retrospective report | Sprint demo; delegate tasks to team members
| Do you have any obstacles? |  |  | Had to focus on another class, pushing back report until tomorrow
Jeremy Freeman | What did you complete yesterday? |  |  |  | Continued study of Django/React/Web development | Cloned team's github repo locally, continued study of Django/React/Web development
| What will you work on to complete today? |  |  | Continued study of Django/React/Web development, studying how backend and frontend connect | Meet with team to review contributions and prepare for spring demo, continued study of Django/React/Web development | Sprint demo in class, finally got server up and running, continued study of Django/React/Web development
| Do you have any obstacles? | Spring break, traveling | Spring break, traveling | Still new to web development, trying to connect everything | Still new to web development, trying to connect everything | Still new to web development, trying to connect everything

## Sprint 4 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Have the Profile page and Setting page ready. Try to come up with the Listing page if possible.
Scrum Master this week: Vorrapard Kumthongdee
Week: 3/28/24 - 4/3/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Sprint 3 in-class Demo. Delegated user stories for Sprint 4. Created system to migrate sprint backlog using Github issues. | More Tutorials. Figured out difference between using Webpack to bundle JS components and Create React App |  |  | Learned alternative framwork our team is using.
| What will you work on to complete today? | Finshing learning Django serializers and DOM routing. | Need to review Github tutorial and how to manage new branch creation and merging with main and completing pull requests. |  | Review other team member's commits to better understand the framework and how the different files/components integrate. | Attend class to learn more about Django.
| Do you have any obstacles? | Limited knowledge on different setups of Django and React and reconoling differences between teams project setup and the setup in my tutorials |  |  | Still confused about the flow between models, serializers, and views. Need to learn how our project uses axios to send requests to the backend API. | Class was cancelled. Will have to address my questions another way.
Vorrapard Kumthongdee | What did you complete yesterday? | Pushed User profile into Github | Had a frontend-page for profile page and setting page | Had a backend code that's not running yet but front end displays correctly | Created a front-end part for listing page + create listing function that is not working yet | Had a listing page and create listing function ready in the front-end.
| What will you work on to complete today? | Design User profile page and profile setting page | Try to connect backend | Design listing page | Fix the create listing function for frontend | Mess with the backend for listing page
| Do you have any obstacles? | Can't yet display/run the user profile becase data need to be fetched - need to write data fetching function in backend | Code can run but data is not fetched correctly | Leave the backend connecting part for Faiyaad | Lissting page is not currently displying the list because the backend part is not working | It says that the backend is sending back data in HTML (not JSON as expected in the front-end request)
Faiyaad Hossain | What did you complete yesterday? | Sprint Demo |  | Created issues and milestones on Github with team
| What will you work on to complete today? | Review team's pull requests | Meet with team to discuss sprint 4 goals | Work on connecting backend/frontend for user account settings/profile |  | Project for another class
| Do you have any obstacles? |  |  |  | Project for another class | Class canceled, sprint continues
Jeremy Freeman | What did you complete yesterday? | Sprint demo in class, finally got server up and running, continued study of Django/React/Web development | Continued study of Django/React/Web development | Plan layout of homepage | Watch react tutorial, create search bar for homepage front end | Connect search bar with placeholder data that will eventually be listings
| What will you work on to complete today? | Continued study of Django/React/Web development | Plan layout of homepage | Watch react tutorial, create search bar for homepage front end | Connect search bar with placeholder data that will eventually be listings | Class canceled, sprint continues
| Do you have any obstacles? |  |  | Still don't have much experience with HTML, CSS, React

## Sprint 4 - Week 2
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Have the Profile page and Setting page ready. Try to come up with the Listing page if possible.
Scrum Master this week: Vorrapard Kumthongdee
Week: 4/4/24 - 4/10/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Review Sprint goals. |  | Created RoomListing serializer. Pulled updates from github to local main. | Began listing CRUD views. | Almost finished listing views and serializers.
| What will you work on to complete today? | Resolve questions regarding Django functionality not clear from the tutorial I used. | Start creating RoomListing Serializer. | Start creating the CRUD views for listings (creating new listings, reading them, updating, and deleting) | Finish CRUD views for listings and finish serializers. Update urls paths to match the API endpoints designated on the frontend actions. Meet with team ahead of the upcoming Spring demo and to go over sprint retrospective. | Attend class and present Sprint 4 demo with team.
| Do you have any obstacles? |  |  |  | Not entirely sure how to use React axios to send requests to API endpoints
Vorrapard Kumthongdee | What did you complete yesterday? | Complete a frontend display page | Had a listing database and the api in the backend | Nothing done | Still couldn't fix the bug | Finally fixed the JSON bug - it was actually the API name calling that's not matching. Before the listingsActions.js called api/listings now api/listings/
| What will you work on to complete today? | Connect the API from frontend to backend | Try to get the create listing button back on the listings page | Try ti fix the bug JSON and HTML return from backend | Try ti fix the bug JSON and HTML return from backend | The listing page is displaying now, but there's no data to show so maybe try to add some units
| Do you have any obstacles? | The create listing button is gone | Error: Unexpected token '<', "<!DOCTYPE "... is not valid JSON | - | Failed to parse source map warning (IDK what it means but the frontend still runs) | -
Faiyaad Hossain | What did you complete yesterday? |  |  | Refined DB models | Finished Integrating settings page | Styled user profile/settings pages, finished integration
| What will you work on to complete today? | Project for another class | Continue integration for user profiles | Create API routes for user profile/settings | Continue integrating Profile page, debrief with group | Sprint Demo
| Do you have any obstacles? |  | Database conflicts, schema needs cleaning
Jeremy Freeman | What did you complete yesterday? | Class canceled, sprint continues | Continue work on homepage design, watch more Django tutorials | Continue work on homepage design, watch more Django tutorials | Overwhelmed with project for another class, won't get much done today | Meet with group to review sprint progress and prepare for demo, add button to redirect to listings page, finish updating look of homepage
| What will you work on to complete today? | Continue work on homepage design, watch more Django tutorials | Continue work on homepage design, watch more Django tutorials | Overwhelmed with project for another class, won't get much done today | Meet with group to review sprint progress and prepare for demo, add button to redirect to listings page, finish updating look of homepage | Sprint demo
| Do you have any obstacles? | Still feeling unexperienced with Django and React | Still feeling unexperienced with Django and React |  | Still feeling unexperienced with Django and React

## Sprint 5 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Finalize CRUD for Listings (frontend & backend). Work on search/messaging if possible
Scrum Master this week: Faiyaad Hossain
Week: 4/11/24 - 4/17/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Sprint Demo in-class | Finished the CRUD listing views and pushed the commits to Github. | Had a meeting with our team and allocated work for the final sprint. | Reviewed unit test lecture and example code. | Began unit test implemenation for views.
| What will you work on to complete today? | Complete the CRUD listings issue. | Meet with team to discuss project progress overall and plan for the next sprint | Review unit testing lecture and learn python's unittest module | Begin implementing unit tests to test the backend views and serializerse in Django. | Attend class in anticipation of the end.
| Do you have any obstacles? | Front-end is only including a few select fields in its listing request, so the serializer only has a few required fields. | Don't now how to do unit testing. | Need to learn unittest and assertion commands
Vorrapard Kumthongdee | What did you complete yesterday? | Fix the unit display bug | fetched the latest main, merged them, and pushed the latest listing branch | Created the header button for Inbox and linked it to InboxScreen.js | Finished the front-end part | Finished backend
| What will you work on to complete today? | pushed the branch up to github and pull request | Jump to work with the messaging feature | InboxScreen.js | Implementing backend | try adding some messages and test the system
| Do you have any obstacles? | - | - | Users shouldn't be allowed to view a certain page if not logged in - added to issues on github |  | error - Unauthorized: /api/messages/ "GET /api/messages/ HTTP/1.1" 401 58
Faiyaad Hossain | What did you complete yesterday? | Sprint demo | Reviewed PRs | Organized goals for Sprint 5 | Make "create listing" form | Made changes to the model
| What will you work on to complete today? | Review pull requests from team | Meet with team to discuss next spring goals | Take over listings user story and overhaul backend/frontend | Update listing model in backend to allow multiple images for new listings | Fix foreign key issues and create frontend for viewing listings
Do you have any obstacles?
Jeremy Freeman | What did you complete yesterday? | Sprint demo | Updated homepage branch | Met with team, discussed roles and assigned tasks | Added listings to my local database for functionality testing | Connect search bar dropdown with backend database
| What will you work on to complete today? | Update homepage branch | Meet with team, discuss roles and assign tasks | Add listings to my local database for functionality testing | Connect search bar dropdown with backend database | Fix search bar dropdown
| Do you have any obstacles? |  |  |  | Didn't work initially, had to make sure variable names were matching correctly

## Sprint 5 - Week 2
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Finalize CRUD for Listings (frontend & backend). Work on search/messaging if possible
Scrum Master this week: Faiyaad Hossain
Week: 4/18/24 - 4/24/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Went to class. | Finished the view test cases | Began implementing the serializer test cases. | Pulled the last main branch to review recent commits and merged into my local main | Met with team to discuss next week additions for our final project delivery.
| What will you work on to complete today? | Finish the views test cases. | Start the serializer test cases. | n/a | Learn how to make mocks so the test cases can be ran. Meet with team at night to discuss progress. Plan for the sprint demo tomorrow and the final week of development. | Attend class with Sprint Demo and Sprint Retrospective
| Do you have any obstacles? | Need to create a database mock in order to test the views using the unittest assertions. | Need to learn how to make mock to use the test cases.
Vorrapard Kumthongdee | What did you complete yesterday? | Got an error when testing the messaging system | Tried implementing profile image | Created the ProfileImageUpload.js frontend part for user to upload profile image. Waiting for the backend part | pull request | Pulled the dev branch but couldn't migrate the backend. Tried install requirements.txt and got error
| What will you work on to complete today? | Move to profile page. I'll try to implement the profile picture | I'll wait for Faiyaad to finish the listing images part, then adapt to user's profile | pull request the messaging system and user-unauthorized page viewing | pull the merged dev/main brance to run the server on my environment and imprelemt more on the messaging system | I fixed the error by updating my python to 3.12
| Do you have any obstacles? | Profile picture is actually harder than I expected. We need another backend to store image for user? | - | - | - | Now I can't migrate because of the foreign key mismatch
Faiyaad Hossain | What did you complete yesterday? | Fixed listing/listingphoto model and created frontend layout for viewing listings | Added feature for editing/deleting listings | Added email verification |  | Team meeting/sprint recap
| What will you work on to complete today? | Make frontend for editing/deleting listings | Add email verification and authentication constraints | N/A | Meet with team to recap sprint and create retrospective report | Sprint demo
| Do you have any obstacles? |  |  | Occupied by another class project | Occupied by another class project
Jeremy Freeman | What did you complete yesterday? | Fixed search bar dropdown | Worked on work for another class | Rework search button so that it doesn't just redirect to listings but actually performs search on listings page | Revise on-click behavior for search bar listings dropdown so that it also searches correctly (instead of providing an alert) | Meet with team, review sprint, prepare for sprint demo
| What will you work on to complete today? | Work on work for another class | Rework search button so that it doesn't just redirect to listings but actually performs search on listings page | Revise on-click behavior for search bar listings dropdown so that it also searches correctly (instead of providing an alert) | Meet with team, review sprint, prepare for sprint demo | Sprint demo
| Do you have any obstacles? | Worked on work for another class

## Sprint 6 - Week 1
CS-GY 6063 Springs Start right after class and end on at the beginning of next class with the Sprint Demo |  | Sprint Goal for this Sprint: Finalize reaming user stories in MVP. Finish on search/messaging features. Implement Unit Testing
Scrum Master this week: Faiyaad Hossain
Week: 4/25/24 - 5/1/24
Person | Question | Thursday | Friday | Monday | Tuesday | Wednesday - Demo Day
Alec Pippas | What did you complete yesterday? | Sprint 5 Product Demo in class. |  | Finished learning Django TestCase and successfully reimplemented tests for profile views. Finished listing tests.
| What will you work on to complete today? | Discuss with team regarding expectations for the final week. | Learn Django TestCase and change old tests using Python's unittest module. Start additional tests | Meet with team tonight to review final commits and prepare all the materials for the final project.
| Do you have any obstacles? | Have to modify my tests to utilize Django's TestCase module which provides a simple solution for database mocking and an interface for simulated client actions (GET/POST requests.) | Did not have time to start writing new tests for listings. Will work on it over the weekend. | Need to write independent course and self-reflection still
Vorrapard Kumthongdee | What did you complete yesterday? | Tried to fixed the backend migration | Got the up-to-date app to work on my environment | Frontend | Rechecked all the Models, Serializers, Views, urls. Everything should work
| What will you work on to complete today? | Reclone the project | Frontend part. Make it looks similar to other page (background etc) | Backend - try to fix the error unauthorized when sending api from message | Backend - try to fix the error unauthorized when sending api from message
| Do you have any obstacles? | It actually helps. I think the problem was Django got confused between the last migration from python 3.7 and the new python 3.12 | - | Can't figure out where the error comes from. | Might not finish before the demo.
Faiyaad Hossain | What did you complete yesterday? | Sprint Demo | Added Comment/Favorite Feature |  | Handle final Merge Conflicts from team members and work on powerpoint/final report
| What will you work on to complete today? | Work on adding Comment/Favorite Feature | Working on a project for another class | Working on a project for another class | Finalized powerpoint, github, and report | Final Demo
| Do you have any obstacles? | Project deadline for another class
Jeremy Freeman | What did you complete yesterday? | Sprint demo | Overwhelmed with other final project | Overwhelmed with other final project | Merge search bar functionality, troubleshoot errors after resolving merge conflicts, meet with team to review project and tie up loose ends | Run project, test features and make sure everything is working properly, complete write up, prepare for final demo
| What will you work on to complete today? | Overwhelmed with other final project | Overwhelmed with other final project | Merge search bar functionality, troubleshoot errors after resolving merge conflicts, meet with team to review project and tie up loose ends | Run project, test features and make sure everything is working properly, complete write up, prepare for final demo | Final demo
| Do you have any obstacles? | Overwhelmed with other final project | Overwhelmed with other final project | Had to reclone the project, there was an issue with the backend